Team 8 – Executive Summary

Capstone Kickoff Meeting (March 12)

1. Purpose

The team met to introduce backgrounds, discuss potential capstone directions, and align on how to move forward. The discussion confirmed that the assignment is highly open-ended and that our priority now is narrowing to a focused, feasible project rather than generating additional ideas.

2. Key Outcomes

Primary Direction Identified

The team aligned most strongly around a college admissions analytics project using publicly available education datasets (IPEDS/Common Data Set).

Potential implementations discussed:

- Predict enrollment likelihood across institutions

- Recommend schools based on applicant profile inputs

- Develop a simple interface for uploading transcripts/resumes

- Include alternative outcomes such as trade schools

Key constraint identified:

- Public datasets lack individual rejected applicant data, limiting certain modeling approaches

👉 Overall: strongest balance of feasibility, rigor, and scope alignment.

Secondary Ideas (Lower Priority)

Property Tax Protest Tool

- Clear real-world use case but heavier data acquisition burden

Infrastructure Optimization (Highways)

- Interesting concept but least developed and highest uncertainty

👉 Both remain viable backups but are not preferred directions.

3. Recommended Project Direction

Working Concept

Data-Driven College Match: A Predictive Decision-Support Tool Using Open Institutional Data

Proposed Execution Approach

Phase 1 – Data Pipeline

- acquire IPEDS/CDS datasets

- clean, merge, engineer features

Phase 2 – Modeling

- logistic regression baseline

- random forest comparison

- optional clustering for institutional archetypes

Phase 3 – Decision Support Output

- score + rank schools by fit

- optional GenAI explanation layer

Phase 4 – Visualization

- dashboards highlighting trends, clusters, and recommendations

👉 This scope delivers strong analytical depth without unnecessary complexity.

4. Alignment With Prior Coursework

Core Techniques (Primary Focus)

Machine Learning (Python)

- predictive modeling + evaluation

Statistics / Multivariate

- correlations, PCA or clustering

Business Intelligence

- dashboards + storytelling

👉 These satisfy most rubric expectations independently.

Supporting Techniques (Selective Use)

Database Concepts – structured storage workflow
Scripting Languages – full pipeline automation

👉 Adds rigor with minimal effort.

Optional Additions

Generative AI – explanation layer only
Time Series – trend visuals if useful
Big Data Strategy/Security – discussion framing

👉 Avoid overengineering beyond these touches.

5. Preliminary Role Alignment

Based on strengths discussed:

- JD: writing, synthesis, framing, visuals direction

- Amanda: modeling + technical execution

- Pedro: domain expertise + data sourcing

- Serena: dashboards + documentation

👉 Balanced workload distribution.

6. Next Steps

Immediate

- review IPEDS/CDS datasets

- brainstorm feasible modeling angles

Short-Term

- meet with professor to confirm expectations

Before Next Checkpoint

- finalize scope

- assign responsibilities

- begin data prep

Bottom Line

We already have strong alignment and sufficient tools to execute successfully. The primary risk now is overengineering rather than underperformance. Our focus should be locking scope quickly and executing efficiently.